## Sheet28
Production Schedule
Product Quantity 9 |  | Completed 1 |  | In Production 5 |  |  | Order Number |  | Order Quantity |  | Produced | Progress | Delivery Date
[7 empty] | 1235 |  | 1000 |  | 400 | 40% | 22/5/21
Customer Name | Order Number | Product Name | Specification | Order Quantity | Unit | Production Daily Output | Start Date | Estimated Completion | Production Produced | (Days) | Production Progress | Audio Fat | Remaining Days | Responsible Person
Rice Husk | 123 | Phone Case | pcs | 2000 | pcs | 500 | 5/11 | 5/16 | 2000 | 4 | 100% | May 20 | 1 | Mumu
Rice Husk | 1235 | Battery | pcs | 1000 | pcs | 400 | 5/15 | 5/18 | 400 | 2.5 | 40% | May 21 | 2 | Mumu
Rice Husk | 1236 | Phone Case | pcs | 800 | pcs | 400 | 5/16 | 5/19 | 480 | 2 | 60% | May 21 | 2 | Mumu
Rice Husk | 1237 | Battery | pcs | 700 | pcs | 300 | 5/17 | 5/20 | 360 | 2.3 | 51% | May 22 | 3 | Mumu
Rice Husk | 123 | Phone Case | pcs | 600 | pcs | 230 | 5/18 | 5/2 | 300 | 2.6 | 50% | May 23 | 4 | Mumu
Rice Husk | 1239 | Battery | pcs | 504 | pcs | 200 | 5/19 | 5/22 | 150 | 25 | 30% | May 24 | 5 | Mumu
Rice Husk | 1240 | Phone Case | pcs | 505 | pcs | 150 | 5/20 | 5/24 |  | 3.4 | 0% | May 25 | 6 | Mumu
Rice Husk | 1241 | Battery | pcs | 506 | pcs | 150 | 5/21 | 5/25 |  | 3.4 | 0% | May 26 | 7 | Mumu
Rice Husk | 1242 | Phone Case | pcs | 507 | pcs | 200 | 5/22 | 5/25 |  | 2.5 | 0% | May 27 | 8 | Mumu