## Large Plan
Microvast Power Systems (Huzhou) Co., Ltd.
Production Schedule (Large)
Department: | Cell Manufacturing Department | [12 empty] | 2013 |  | Year | 11 | Month
Order | Customer | Product Name | Specification | Quantity (pcs) | Delivery Date | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | …… | 30 | 31
Project
123 | Microvast PACK | Pouch Cell | MV06203127NTP-10Ah | 10000 | 12.22 | Planned Output
124 | X | Pouch Cell | MV06203127NTP-6Ah | 5000 | 12.25 | Planned Output
Planned Output

## Mid Plan
Microvast Power Systems (Huzhou) Co., Ltd.
Production Schedule (Mid)
Workshop: | Workshop One | [6 empty] | Week |  | Month |  | Day | to | 日 | Month |  | Day |  | 日
Order | Customer | Product Name | Specification | Quantity (pcs) | Delivery Date | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | …… | 30 | 31
Project
123 | Microvast PACK | Pouch Cell | 10Ah | 10000 | 12.22 | Planned Output | 1: 5000; 2: 5000
[6 empty] | Actual Output | 1: 4850; 2: 5050
[6 empty] | Shortage | 1: -150; 2: 50
124 | X | Pouch Cell | 6Ah | 5000 | 12.25 | Planned Output | 3: 5000
[6 empty] | Actual Output | 3: 5000
[6 empty] | Shortage | 3: 0

## Sheet1
xxx Company March 19, 2012 -- March 25, 2012 Production Plan
40986
Serial No. | Project Name | Item | Total Project Volume (T) | Quantity (pieces) | This Month's Completed Volume (T) | Material Status | March 12 -- March 18 Plan | Remarks
1 | Huazhi Plaza | TD22-25 Floors | 30 | 22 | 30 | Materials have arrived | Fully completed
|  | TD26-29 Floors | 90 | 54 | 90 | Some materials missing | Fully completed
|  | QL4- D1, D2, B1 Steel Columns | 90 | 54 | 90 | Materials planned | Cutting and assembly completed, ready for riveting
|  | QL4- D1, D2, B1 Steel Beams | 250 | 28 | 220 | Materials have arrived | Fully completed
|  | QL4- C3, C4 Steel Columns |  | 54 |  | Materials have arrived | Fully completed
|  | QL4- C3, C4 Steel Beams | 240 | 46 | 240 | Materials have arrived | Fully completed
|  | QL4- C3, C4 Steel Beams |  | 37 |  | Materials have arrived | C3 area completed, C4 area partially completed
2 | Fulin Metropolis | 2F Steel Columns | 95 | 23 | 40 | Materials not complete | Start cutting and assembly, produce finished products as planned
3 | Chuanqi New Energy Vehicles | Steel Columns, Steel Beams | 330 | 330 | 60 | Materials have arrived | Fully completed
|  | Column Bracing/Horizontal Bracing/Tie Rod | 30 | 20 | 30 | Materials have arrived | Knee braces, auxiliary beams, other components, and accessories fully completed
|  | Crane Beams/Truss System | 150 | 96 |  | Materials not arrived | Depends on material and arrangement
4 | Sichuan Jianhua Pipe Pile | B Workshop Crane Beams and Trusses | 130 | 110 | 90 | Materials have arrived | Truss angle steel completed
|  | B Workshop Platform Beams, Columns |  | 20 |  | Materials have arrived | Fully completed
|  | Skylight Frame, Mixing Building |  |  |  | Materials have arrived | Mixing building completed
|  | A, B Yard Crane Beams | 160 | 280 |  | Materials have arrived
|  | A, B Yard Trusses and Bracing | 113 |  | 50 | Materials have arrived | Remaining part of 24-51 line inter-column bracing completed
5 | FAW-Volkswagen No. 7 | Steel Columns and Beams | 260 |  | 260 | Some materials missing
|  | Column Bracing, Tie Rod, Corner Bracing | 30 |  | 30 | Materials have arrived | Inter-column bracing and column top tie rods fully completed
6 | Jiannanchun | Crane Beams/Truss System | 275 | 220 | 220 | Materials have arrived | Interspersed riveting and welding started
|  | 25-30 Axis Steel Frame | 30 | 78 |  | Materials have arrived
7 | Jiannanchun | Small Workshop | 6 |  | 6 | Materials have arrived | Completed and shipped by March 20
8 | Raffles City | Small Steel Columns | 10 | 65 | 10 | Materials have arrived | Steel sections and supplementary small steel columns completed and shipped
Total |  |  | 2319 |  | 1466