## 0300 System
Risk ID | Item Description | Function | Tech. Class | Novel Aspects | Failure Mode | Failure Effects (Local, WEC, System) | Failure Cause(s) | Initial Mode of Operation | Risk Reduction Design | Preventative Detection | Post Failure Detection | Post Failure Repair Strategy (automated, manual)
310-1 | Motor Drive | Convert Motor Generator Voltages to DC voltage for transmission and storage. | 2 | Marine application, loading | Short or Open Circuit | Loss of Power Production, PTO Controlled Shutdown may or may not be possible | Corrosion Induced Short Circuit | Normal | Marine Rated system for corrosion protection, controlled nacelle environment | Visual Inspection, SCADA Detection of Flooding | SCADA Diagnosis | In-Situ Inspection, Repair or Replacement
310-2 | Motor Drive | Convert Motor Generator Voltages to DC voltage for transmission and storage. | 2 | Marine application, loading | Short or Open Circuit | Loss of Power Production, PTO Controlled Shutdown may or may not be possible | Improper Installation or Manufacturing defect | Normal | V&V (QA/QC) | Visual Inspection | SCADA Diagnosis | In-Situ Inspection, Repair or Replacement of faulty component
310-3 | Motor Drive | Convert Motor Generator Voltages to DC voltage for transmission and storage. | 2 | Marine application, loading | Short or Open Circuit | Loss of Power Production, PTO Controlled Shutdown may or may not be possible | Vibration or Buoy Motion induced failure | Normal | V&V (QA/QC), Proper selection of bus attachment system | Visual Inspection | SCADA Diagnosis and visual inspection | In-Situ Inspection, Repair or Replacement of faulty component or mounting
310-4 | Motor Drive | Convert Motor Generator Voltages to DC voltage for transmission and storage. | 2 | Marine application, loading | Short Circuit | Loss of Power Production, PTO Controlled Shutdown may or may not be possible | Flooding Induced Failure (contact with water not corrosion) | Normal | System level isolation from water ingress, Marine rated Components, System level seperation of equipment. | Visual Inspection, SCADA Detection of Flooding | SCADA Diagnosis and visual inspection | Removal of Bouy from Water for dry repair or dry dock overhaul
330-1 | Energy Storage | Power smoothing for continuous power flow over umbilical to subsea battery, and to support local payload power needs | 2 | Marine application, loading | Faulted Energy Storage | Loss of Power smoothing, Reduced Damping, Reduction in power production to the battery | Corrosion induced failure short/open circuit | Normal | Marine Rated system for corrosion protection, controlled nacelle environment | Visual Inspection, SCADA Detection of Flooding | SCADA Diagnosis | In-Situ Inspection, Repair or Replacement
330-2 | Energy Storage | Power smoothing for continuous power flow over umbilical to subsea battery, and to support local payload power needs | 2 | Marine application, loading | Faulted Energy Storage | Loss of Power smoothing, Reduced Damping, Reduction in power production to the battery | Improper Installation or Manufacturing defect | Normal | V&V (QA/QC) | Visual Inspection | SCADA Diagnosis | In-Situ Inspection, Repair or Replacement of faulty component
330-3 | Energy Storage | Power smoothing for continuous power flow over umbilical to subsea battery, and to support local payload power needs | 2 | Marine application, loading | Faulted Energy Storage | Loss of Power smoothing, Reduced Damping, Reduction in power production to the battery | Vibration or Buoy Motion induced failure | Normal | V&V (QA/QC), Proper selection of bus attachment system | Visual Inspection | SCADA Diagnosis and visual inspection | In-Situ Inspection, Repair or Replacement of faulty component or mounting
330-4 | Energy Storage | Power smoothing for continuous power flow over umbilical to subsea battery, and to support local payload power needs | 2 | Marine application, loading | Faulted Energy Storage | Loss of Power smoothing, Reduced Damping, Reduction in power production to the battery | Flooding Induced Failure (contact with water not corrosion) | Normal | System level isolation from water ingress, Marine rated Components, System level seperation of equipment. | Visual Inspection, SCADA Detection of Flooding | SCADA Diagnosis and visual inspection | Removal of Bouy from Water for dry repair or dry dock overhaul
330-5 | Energy Storage | Power smoothing for continuous power flow over umbilical to subsea battery, and to support local payload power needs | 2 | Marine application, loading | Fire/Smoke | Loss of Power smoothing, Reduced Damping, Reduction in power production to the battery | Fire/Smoke induced failure | Normal | Safety and Emergency system smoke alarm, overcurrent protection | Visual Inspection, SCADA Detection of Fire | SCADA Diagnosis and visual inspection | In-Situ Inspection, In-Situ Repair or Replacement of faulty component or Removal of Bouy from Water for dry repair or dry dock overhaul
330-5 | Energy Storage | Power smoothing for continuous power flow over umbilical to subsea battery, and to support local payload power needs | 2 | Marine application, loading | Faulted Energy Storage | Loss of Power smoothing, Reduced Damping, Reduction in power production to the battery | Failure of Capacitor internally | Normal | temperature monitoring, charge control. V&V (QA/QC) | Visual Inspection, SCADA Detection | SCADA Diagnosis and visual inspection | In-Situ Inspection, Repair of faulty component
340-1 | Umbilical Power Converter | Control power flow over umbilical to subsea battery | 2 | Marine application, loading | Short or Open Circuit | Loss of power transmission across umbilical | Corrosion Induced Short Circuit | Normal | Marine Rated system for corrosion protection, controlled nacelle environment | Visual Inspection, SCADA Detection of Flooding | SCADA Diagnosis | In-Situ Inspection, Repair or Replacement
340-2 | Umbilical Power Converter | Control power flow over umbilical to subsea battery | 2 | Marine application, loading | Short or Open Circuit | Loss of power transmission across umbilical | Improper Installation or Manufacturing defect | Normal | V&V (QA/QC) | Visual Inspection | SCADA Diagnosis | In-Situ Inspection, Repair or Replacement of faulty component
340-3 | Umbilical Power Converter | Control power flow over umbilical to subsea battery | 2 | Marine application, loading | Short or Open Circuit | Loss of power transmission across umbilical | Vibration or Buoy Motion induced failure | Normal | V&V (QA/QC), Proper selection of bus attachment system | Visual Inspection | SCADA Diagnosis and visual inspection | In-Situ Inspection, Repair or Replacement of faulty component or mounting
340-4 | Umbilical Power Converter | Control power flow over umbilical to subsea battery | 2 | Marine application, loading | Short Circuit | Loss of power transmission across umbilical | Flooding Induced Failure (contact with water not corrosion) | Normal | System level isolation from water ingress, Marine rated Components, System level seperation of equipment. | Visual Inspection, SCADA Detection of Flooding | SCADA Diagnosis and visual inspection | Removal of Bouy from Water for dry repair or dry dock overhaul
370-1 | Emergency Resistor | Electrical Resistor for dissipating power in over voltage situations | 2 | Marine application, loading | Open circuit occurs in resistor under load | Overvoltage from loss of emergency resistor could damage Electrical Insulation, and result in shorts or open circuits in other components, loss of PTO damping may lead to structural fatigue | Failure due to Corrosion, Inproper Mounting, Vibration, overheating, or over-current | Normal | Marine-rated resistor module, design to provide sufficient cooling and vibration damping | SCADA - temperature, vibration, and current monitoring | SCADA - PTO controller error diagnostics, physical inspection/test | In-Situ Inspection, Repair or Replacement of faulty component
380-1 | Motor Bus | Electrical Connection between Generating Motor and Motor Drive | 2 | Marine application, loading | Short Or Open Bus | Loss of Power Generation, PTO Controlled Shutdown | Corrosion Induced Short Circuit | Normal | Marine Rated system for corrosion protection, controlled nacelle environment | Visual Inspection, SCADA Detection of Flooding | SCADA Diagnosis | In-Situ Inspection, Repair or Replacement
380-2 | Motor Bus | Electrical Connection between Generating Motor and Motor Drive | 2 | Marine application, loading | Short Or Open Bus | Loss of Power Generation, PTO Controlled Shutdown | Improper Installation or Manufacturing defect | Normal | V&V (QA/QC) | Visual Inspection | SCADA Diagnosis | In-Situ Inspection, Repair or Replacement of faulty component
380-3 | Motor Bus | Electrical Connection between Generating Motor and Motor Drive | 2 | Marine application, loading | Short Or Open Bus | Loss of Power Generation, PTO Controlled Shutdown | Vibration or Buoy Motion induced failure | Normal | V&V (QA/QC), Proper selection of bus attachment system | Visual Inspection | SCADA Diagnosis and visual inspection | In-Situ Inspection, Repair or Replacement of faulty component or mounting
380-4 | Motor Bus | Electrical Connection between Generating Motor and Motor Drive | 2 | Marine application, loading | Short on Bus | Loss of Power Generation, PTO Controlled Shutdown | Flooding Induced Failure (contact with water not corrosion) | Normal | System level isolation from water ingress, Marine rated Components, System level seperation of equipment. | Visual Inspection, SCADA Detection of Flooding | SCADA Diagnosis and visual inspection | Removal of Bouy from Water for dry repair or dry dock overhaul
380-5 | DC Bus | Common electrical connection between motor drive, local energy storage, and umbilical power converter | 2 | Marine application, loading | Short Or Open Bus | Loss of Power Generation, PTO Controlled Shutdown | Corrosion Induced Short Circuit | Normal | Marine Rated system for corrosion protection, controlled nacelle environment | Visual Inspection, SCADA Detection of Flooding | SCADA Diagnosis | In-Situ Inspection, Repair or Replacement
380-6 | DC Bus | Common electrical connection between motor drive, local energy storage, and umbilical power converter | 2 | Marine application, loading | Short Or Open Bus | Loss of Power Generation, PTO Controlled Shutdown | Improper Installation or Manufacturing defect | Normal | V&V (QA/QC) | Visual Inspection | SCADA Diagnosis | In-Situ Inspection, Repair or Replacement of faulty component
380-7 | DC Bus | Common electrical connection between motor drive, local energy storage, and umbilical power converter | 2 | Marine application, loading | Short Or Open Bus | Loss of Power Generation, PTO Controlled Shutdown | Vibration or Buoy Motion induced failure | Normal | V&V (QA/QC), Proper selection of bus attachment system | Visual Inspection | SCADA Diagnosis and visual inspection | In-Situ Inspection, Repair or Replacement of faulty component or mounting
380-8 | DC Bus | Common electrical connection between motor drive, local energy storage, and umbilical power converter | 2 | Marine application, loading | Short on Bus | Loss of Power Generation, PTO Controlled Shutdown | Flooding Induced Failure (contact with water not corrosion) | Normal | System level isolation from water ingress, Marine rated Components, System level seperation of equipment. | Visual Inspection, SCADA Detection of Flooding | SCADA Diagnosis and visual inspection | Removal of Bouy from Water for dry repair or dry dock overhaul