## Sheet1
| DAILY MORNING DISCUSSION | [6 empty] | Meeting.# 01
Meeting Date: 24 Oct, 24
S.No | Job Description | Equipment/Location | Job Raised by | Job Assigned to | Expected Time to Complete | Job Assigning Date | Job Completion Date | Status | Remarks
1 | Pre Heating Pump Testing | JL1 | Electrical Department | Electrical Department | 1 Hour | 2024-10-24 | 2024-10-24 | Completed | Tests performed but pump not working
2 | Internet Cable Laying | Control Room/Admin Area | IT Department | Electrical Department | 1 Hour | 2024-10-24 | 2024-10-24 | Completed
3 | Fiber Tank Pump Control Issue | Basement | HVAC Department | Electrical Department | 2 hours | 2024-10-24 | 2024-10-24 | Completed
4 | Heat Exchanger Washing | JL1 | Mechanical Department | Mechanical Department | 2 days | 2024-10-24 |  | Completed
5 | Exhaust Silencer Modification | JL1 | Mechanical Department | Mechanical Department |  | 2024-10-24 |  | Work in Progress
6 | Pre Chamber Sleeve Replacement | JL1 | Mechanical Department | Mechanical Department | 2 days | 2024-10-24 |  | Completed
7 | Jacket Water Circuit Flushing | JL4 | Mechanical Department | Mechanical Department | 2 days | 2024-10-24 |  | Completed
8 | Core Cutting | Absorption Chiller Area | Automation Department | Mechanical Department | 1 day | 2024-10-24 | 2024-10-24 | Completed
9 | PMS of Centrifugal Chiller No 3, Condensor no 5 | Chiller No 5 | HVAC Department | HVAC Department | 1 day | 2024-10-24 | 2024-10-24 | Completed
10 | Programming Work in Heat Exchanger Temperature Sensor | JL4 | HVAC Department | Automation Department | 1 day | 2024-10-24 | 2024-10-24 | Completed
11 | Cooling Tower Area Cleaning | Cooling Tower | HSE Department | Admin Department | 2 days | 2024-10-24 |  | Completed
12 | Scrap Area Visit/Arrangements | Scrapyard | HSE Department | Admin Department | 1 day | 2024-10-24 |  | Completed
13 | SIPA Certified Vendors Visit |  | HSE Department | Admin Department | 2 days | 2024-10-24 |  | Completed
14 | LOTTO Meeting | Conference Room | HSE Department | HSE Department | 2 hours | 2024-10-24 | 2024-10-24 | Completed