## Sheet1
| DAILY MORNING DISCUSSION | [6 empty] | Meeting.# 02
Meeting Date: 25 Oct, 24
S.No | Job Description | Equipment/Location | Job Raised by | Job Assigned to | Expected Time to Complete | Job Assigning Date | Job Completion Date | Status | Remarks
1 | Installation of JL1's Pre Heating Pump in JL4 | JL4 | Electrical Department | Electrical Department | 2 hours | 2024-10-25 |  | Completed | In Testing Phase
2 | Maintenance of Club House | Club House | Electrical Department | Electrical Department | 1 day | 2024-10-25 |  | Completed
3 | Absorption Hot Water Pump 1 & 2 maintenance | Abs Chiller Area | HVAC Department | HVAC Department | 1 day | 2024-10-25 |  | Completed
4 | Centrifugal Chiller No 4 PMS | Chiller No 4 | HVAC Department | HVAC Department | 1 day | 2024-10-25 |  | Completed
5 | Replacement of RO Multimedia | RO | HVAC Department | HVAC Department | 3 days | 2024-10-25 |  | Work in Progress | Multimedia will be arranged from Kathore
6 | Mess Area Dispensor Repairing | Mess Area | Admin Department | Admin Department | 2 days | 2024-10-25 |  | Work in Progress
7 | Fire Extinguishers Numbering | All Locations | HSE Department | Mechanical Department | 2 days | 2024-10-25 |  | Work in Progress
8 | Fire Extinguishers Area Cleaning | All Locations | HSE Department | Mechanical Department | 2 days | 2024-10-25 |  | Work in Progress
9 | Secondary Containment for Oil Spillage | Store Room | HSE Department | Mechanical Department | 1 days | 2024-10-25 |  | Work in Progress
10 | Points Mapping Activity (Generation Reports) | HVAC | HVAC Department | Automation Department | 2 days | 2024-10-25 |  | Work in Progress