## 26-Oct-2024
DAILY MORNING DISCUSSION | [7 empty] | Meeting.# 03
Meeting Date: 26 Oct, 24
S.No | Job Description | Equipment/Location | Job Raised by | Job Assigned to | Expected Time to Complete | Job Assigning Date | Job Completion Date | Status | Remarks
1 | Thermostate Switch Change on DG-2 | DG-2 | Electrical Department | Electrical Department | 2 hours | 2024-10-26 |  | Work in Progress
2 | Heat Exchanger Boxup in JL-1 | JL-1 | Mechanical Department | Mechanical Department | 1 day | 2024-10-26 |  | Work in Progress
3 | Compensator Fitting in Exhaust Flange (JL-1) | Muffler Room | Mechanical Department | Mechanical Department |  | 2024-10-26 |  | Work in Progress
4 | Cable Laying in Level Transmittor | Raw Water Tank | Automation Department | Automation Department | 2 days | 2024-10-26 |  | Work in Progress
5 | Core Cutting Area Sensor Installation | Absorption Chiller Area | HVAC Department | Mechanical Department |  | 2024-10-26 |  | Work in Progress
6 | Proper Conduiting of Cables in Cooling Tower Area | Cooling Tower | Electrical Department | Electrical Department |  | 2024-10-26 |  | Work in Progress
7 | Absorption Hot Water Pump No 3 PMS | Absorption Chiller Area | HVAC Department | HVAC Department | 1 day | 2024-10-26 |  | Work in Progress
8 | Weekly Checklist Activity | Scrap Area, Cooling Tower, LTM | Admin Department | Admin Department | 1 day | 2024-10-26 |  | Work in Progress | Construction work going on in LTM, Scrap Area visit to be conducted on Wednesday
9 | LTM Transformer Cleaning | LTM | Electrical Department | Electrical Department | 1 day | 2024-10-26 |  | Work in Progress